Website Build Process

Discovery, Design & Delivery

Internal process document — from first contact through to launch and beyond.

Version 3  ·  June 2026

# Contents

1. Overview

2. Phase 1: Discovery

3. Phase 2: Workshop & Strategy

4. Phase 3: Wireframes & Homepage Design

5. Phase 4: Full Design & Content

6. Phase 5: Development & Testing

7. Phase 6: Launch & Handover

8. Post-Launch Support

Appendix A: Discovery Questionnaire

Appendix B: Brand Personality Spectrum

Appendix C: Features Checklist

Appendix D: Competitor Review Template

Appendix E: Go-Live Checklist

# 1. Overview

This document defines the end-to-end process for building a client website. It covers six phases, each with defined outputs and approval gates. No phase begins until the previous phase has been signed off.

The process is designed to be thorough without being slow. Clients see structured progress at every stage. The team knows exactly what is expected and when.

### Process at a Glance

| Phase | What Happens | Output | Sign-off |
| --- | --- | --- | --- |
| 1. Discovery | Discovery call, questionnaire, client brief | Completed questionnaire, client knowledge file | Thomas confirms go |
| 2. Workshop & Strategy | Market research, SEO, visual direction, content audit | Website Workshop Document (PDF) | Client approves direction |
| 3. Wireframes & Homepage | Wireframes, homepage copy, high-fidelity homepage design | Wireframes + homepage mockup + copy | Client picks direction |
| 4. Full Design & Content | All pages designed, all copy written, brand review | Full-site mockups + complete copy deck | Client approves before dev |
| 5. Development & Testing | Build, integrations, QA testing | Staging site (full build) | PM QA + client review |
| 6. Launch & Handover | Go-live checklist, SEO migration, training | Live website + handover doc | Thomas confirms launch |

# 2. Phase 1: Discovery

### Who is involved

PM, Account Manager, CEO (for new clients)

### What happens

Discovery call with the client using the workshop questionnaire (see Appendix A) or the companion PowerPoint deck.

PM writes up call notes and circulates to all relevant agents.

Account Manager creates or updates the client knowledge file in knowledge/clients/.

For new clients, CEO reviews the brief for strategic fit and sets engagement direction.

### Output

Completed questionnaire, client knowledge file, call notes.

### Sign-off

Thomas confirms the project is a go.

# 3. Phase 2: Workshop & Strategy

### Who is involved

Marketing Strategist, SEO Specialist, Copywriter, Creative Director, PM

### What happens

Marketing Strategist analyses the market, competitors, and audience using the discovery notes.

SEO Specialist runs keyword research and identifies search opportunities for the site structure.

Creative Director reviews brand materials and reference sites, sets visual direction.

Copywriter reviews the client's existing language and drafts a tone-of-voice guide if none exists.

PM compiles all findings into a single workshop document.

### Workshop document covers

Website goals ranked by priority

Target audience profiles

Sitemap and page hierarchy (informed by SEO research)

Content requirements per page

Visual direction (mood, references, constraints)

Technical requirements and integrations

Success metrics

### Output

Website Workshop Document (PDF) — sitemap, wireframes, design brief.

### Sign-off

Thomas reviews with client. Client approves direction before any design work starts.

# 4. Phase 3: Wireframes & Homepage Design

### Who is involved

Creative Director, Graphic Designer, Copywriter, Frontend Developer

### What happens

Creative Director produces wireframes for the homepage and two or three key interior pages.

Copywriter writes the homepage copy in full — headlines, body text, calls to action.

Graphic Designer builds a high-fidelity homepage design using the wireframe, copy, and brand direction.

Frontend Developer flags any technical constraints early (animations, interactions, responsive behaviour).

### Output

Wireframes (all key pages) + full homepage design mockup + homepage copy.

### Sign-off

Thomas presents to client. Client picks the direction. Feedback captured and actioned before Phase 4.

# 5. Phase 4: Full Design & Content

### Who is involved

Graphic Designer, Copywriter, Brand Guardian, Creative Director

### What happens

Graphic Designer rolls out the approved homepage direction across all remaining pages.

Copywriter writes copy for every page.

Brand Guardian reviews the full design for consistency — colours, typography, tone, image treatment.

Creative Director does a final review of the complete design package.

Content harvesting document issued — client supplies remaining assets, photography, and copy inputs.

### Output

Full-site design mockups (all pages) + complete copy deck.

### Sign-off

Thomas presents to client. Client approves designs before development begins.

# 6. Phase 5: Development & Testing

### Who is involved

Lead Developer, Frontend Developer, Backend Developer (if needed), WordPress Developer (if WordPress), QA Engineer

### What happens

Lead Developer sets the technical architecture and assigns work.

Frontend Developer builds the site from approved designs — pixel-accurate, responsive, fast.

Backend Developer handles custom functionality, integrations, or database work.

WordPress Developer builds on WordPress/WooCommerce if that is the platform.

QA Engineer tests across devices, browsers, and screen sizes.

### Development stages

1. Homepage and global elements (header, footer, navigation)

2. Interior pages in priority order

3. Functional features (forms, booking, ecommerce, search)

4. Content population and image optimisation

5. QA testing round

### Output

Staging site — full build, all content loaded, all features working.

### Sign-off

PM runs QA review. Thomas reviews staging site. Client reviews and provides feedback. Revisions made before launch.

# 7. Phase 6: Launch & Handover

### Who is involved

Lead Developer, SEO Specialist, Analytics Specialist, Account Manager, PM

### What happens

Pre-launch checklist completed (see Appendix E).

Hosting and domains finalised.

SEO migration plan executed.

Cookie consent and GDPR compliance verified.

All API keys and integrations tested in production.

### Output

Live website, handover document, analytics dashboard access.

### Sign-off

Thomas confirms launch. Account Manager walks the client through the finished site.

# 8. Post-Launch Support

After launch, the Account Manager owns the client relationship. Monthly check-ins cover:

Analytics review (traffic, conversions, top pages)

Content updates or additions needed

Performance monitoring (speed, uptime)

SEO progress against target keywords

Backlog of improvements or new features

Quarterly business review with client

# Appendix A: Discovery Questionnaire

## The Business

Client name:

Primary contact name and role:

What does the business do? (One or two sentences, plain language):

How long have they been operating?

What makes them different from competitors? (In the client's own words):

Who are their main competitors? (Names and URLs):

What's working well for the business right now?

What's not working?

## Goals & Objectives

What are the website's primary goals? (Lead gen / ecommerce / bookings / brochure / recruitment / other):

What is the single most important action a visitor should take?

Macro business objectives over the next few years:

Anything on competitor sites that definitely works?

How will you measure whether the website is successful?

## Current Website

Current website URL:

What's wrong with it? (Slow, outdated, no leads, bad on mobile, can't update):

Specific features needed? (Booking, payments, blog, portfolio, listings):

Do they need to update the site themselves? How often and what content?

Websites they admire (URLs and what they like):

Websites they dislike (URLs and what puts them off):

## Audience Insight

Ideal customer? (Age, location, income, profession):

What type of people? (Roles, personality, male/female split):

What are they looking for on the site?

What sells the company to them? (Expertise, trust, portfolio, price, speed):

Questions customers ask before buying or getting in touch:

Objections or hesitations potential customers have:

Different audience segments the site needs to speak to:

How have people heard about you?

How do customers currently find you? (Google, word of mouth, social, ads, referrals):

How educated are they at first contact? Should the website do more or less educating?

How do they like to make contact? (Phone, email, form, WhatsApp, walk-in):

Best contact method for the team:

## The Brand

Existing brand guidelines? (Logo files, colour palette, fonts, tone of voice):

If no guidelines, describe the brand feel wanted:

Brand colours (hex codes if available):

Open to exploring additional or alternative colours?

Colours or visual elements to avoid:

Logo files provided? (Format: SVG, PNG, AI):

Professional photography available? Open to a shoot?

Imagery style preference? (Photography, illustrations, abstract, icons):

Tone of voice — how do they talk to customers? (Formal, casual, technical, warm):

## Content & Pages

Pages they think they need (list):

Existing copy: keep, rewrite, or start fresh?

Testimonials or case studies available?

Product/service descriptions written?

Certifications, awards, or credentials to feature:

Blog needed? Who writes posts?

Social proof — testimonials, reviews, client logos:

Hierarchy of services — which are most important:

Non-sales goals? (Careers, hiring, investor relations):

## Technical & Practical

Preferred platform (WordPress, custom, Shopify, other):

Existing hosting? Where?

Domain registered? Who controls it?

Integrations needed? (CRM, email, booking, accounting, payments):

Email addresses needed on the domain?

Current SEO rankings? Target keywords?

Google Analytics or Search Console set up?

Cookie consent / GDPR requirements:

## Budget, Timeline & Decisions

Budget range (under €2k, €2-5k, €5-10k, €10k+):

Hard deadline? (Event, season, launch date):

What's driving the timing? Why now?

Who signs off? (Contact only, or partner/board approval):

Done a website project before? What went well or badly?

Preferred communication method? (Email, phone, WhatsApp, video calls):

How involved do they want to be? (Hands-on or hands-off):

# Appendix B: Brand Personality Spectrum

Mark where the brand sits on each scale.

|  | Scale |  |
| --- | --- | --- |
| Personable & Friendly | ← ─────────────── → | Corporate & Professional |
| Adaptable & Flexible | ← ─────────────── → | Careful & Strategic |
| Contemporary & High-Tech | ← ─────────────── → | Classic & Traditional |
| Cutting Edge | ← ─────────────── → | Established & Proven |
| Accessible & Open | ← ─────────────── → | Exclusive & Premium |
| Playful & Bold | ← ─────────────── → | Understated & Refined |

# Appendix C: Features Checklist

## Core

☐  Strong call-to-action buttons

☐  Clean, simple design

☐  Conversion optimised

☐  Showcase products and services

☐  Fully responsive (mobile, tablet, desktop)

☐  SSL certificate / security

☐  Search engine friendly (SEO)

☐  Visually engaging

☐  Fast loading (under 3 seconds)

☐  Easy-to-read copy

☐  Trustmarks (accreditations, associations, testimonials)

☐  Measurable (analytics, conversions)

## Functionality

☐  Cross-browser compatible

☐  Carousel / image gallery

☐  Social media integration

☐  Blog / news section

☐  Live chat / support widget

☐  Contact forms

☐  Site search

☐  External platform integrations

☐  Resource library / downloadable brochures

☐  Email newsletter subscription

☐  Share / print icons

☐  Online booking / payments

☐  Community forum

# Appendix D: Competitor Review Template

Complete one table per competitor reviewed during the workshop.

| Field | Notes |
| --- | --- |
| Competitor name |  |
| URL |  |
| Design approach |  |
| Use of colour |  |
| Photography / imagery style |  |
| Navigation & UX |  |
| What works well |  |
| What we'd avoid |  |

# Appendix E: Go-Live Checklist

☐  All forms submit and notify correctly

☐  SSL certificate active, no mixed content warnings

☐  Mobile and tablet layouts tested

☐  Page speed under 3 seconds on mobile

☐  All images optimised and loading

☐  404 page in place

☐  Favicon and social sharing images set

☐  Analytics tracking firing

☐  Old URL redirects in place (if applicable)

☐  Cookie consent / privacy policy live (if required)

☐  Client has CMS login credentials

☐  SEO: sitemap submitted, meta tags configured

☐  API keys and integrations tested in production

☐  Bug fixes resolved

☐  Scope creep items logged (not silently added)